## Intake
Input Question | Correlates to on Output
Event Name | Row 1
Which BW team members will help you with this event? | Row 5 and Owner column
How many external attendees? | Row 6
Dates | Row 2 and should be used for "deadline" date when computing dates in Deadline column
Can you tell me a rough agenda of the entire time? (team flies in, meetings next day, team flies home, etc) | Row 3
City/Venue | Row 4
Will you need meeting space?
Do you need A/V setup?
Will you need sleeping rooms?
Do you know of any dietary/accessibility needs? | Include answer in cell G27
What is the plan for food (be specific: snacks, meals during meeting time or offsite, grab-go-lunch)
Do you have a prefered layout for the room (classroom, round tables, etc)? | Include answer in cell G21
Do we need a registration or check-in table near the entrance?
Will you need supplies (name tags, pens, sticky notes, etc)?

## Preferred OutPut
Event Name: | {{Include answer from user input}}
Event Dates: | {{Include answer from user input}}
Timeline: | {{Include answer from user input}}
Event Location: | {{Include answer from user input}}
BW Attendees: | {{Include answer from user input}}
External Attendees: | {{Include answer from user input}}
| Task | Owner | Deadline | Status | Existing Resources | Notes
Planning & Admin
| Identify a final date and hold on calendars |  | MM/DD/YY |  | Something like SteerCo template can help schedule (https://docs.google.com/spreadsheets/d/1pP_PnkgTsC00I4yI_4lf2Iixn7LrhmbEOQjDWF_Ny-I/edit?usp=drive_link)
| Communicate date and give travel parameters to rest of project team |  | MM/DD/YY
Agenda & Facilitation
| Draft event agenda and timing |  | MM/DD/YY
| Develop a plan to send prework |  | MM/DD/YY
Contracts |  |  |  |  | Cvent (cvent.com/venues) can help research and submit venue RFPs | Reminder about BW contracts policy
| Research and shortlist 5 event venues |  | MM/DD/YY |  |  | A table/comparison tool within your PM doc can be helpful
| Finalize venue choice and solicit final contract |  | MM/DD/YY
| Submit venue contract for BW review |  | MM/DD/YY
| Secure signatures and finalize venue contract |  | MM/DD/YY
Meeting Space & A/V
| Confirm meeting room setup and A/V needs |  | MM/DD/YY |  |  | {{Include answer from Intake Question 13}}
| Solicit and finalize any BEOs |  | MM/DD/YY |  | Reminder about BW contracts policy
Lodging
| Ensure sleeping rooms are part of venue contract |  | MM/DD/YY |  |  | Hotels usually require 10+ rooms for room blocking. BW typically responsible to fill 80% of those rooms. Rooms can be paid all on one card (submit master booking list), or hotel can generate booking link for guests to book/pay on their own
| Book sleeping rooms for attendees |  | MM/DD/YY
| Share lodging confirmation details |  | MM/DD/YY
Meals |  |  |  |  | EZ Cater can help you with group orders and catering (ezcater.com) | {{Include answer from Intake Question 11}}
| Solicit dietary needs from external attendees |  | MM/DD/YY
| {{Include answer from Intake question 12}} |  | MM/DD/YY
| Plan menus accommodating dietary needs |  | MM/DD/YY |  | There's an existing prompt in our dashboard that can help!
| Research offsite dinner venues |  | MM/DD/YY |  | There's an existing prompt in our dashboard that can help!
| Finalize venue choice and solicit final contract |  | MM/DD/YY |  |  | Reminder about BW contracts policy
| Submit venue contract for BW review |  | MM/DD/YY
| Secure signatures and finalize venue contract |  | MM/DD/YY
| Solicit and finalize any BEOs |  | MM/DD/YY
Materials & Shipping
| Prepare name badges and materials |  | MM/DD/YY
| Order fidget toys or other engagement tools |  | MM/DD/YY
| Ship supplies to venue |  | MM/DD/YY
Onsite
| Gather and list Onsite Contact name and number |  | MM/DD/YY
Post-Event
| Conduct internal debrief and lessons learned |  | MM/DD/YY
| Ensure all expenses are accounted for |  | MM/DD/YY |  |  | A budget tracker within your PM doc is helpful

## Test Event
Event Name: Test Event
Event Dates: March 4-5 2026
Timeline: 03/12/26
Event Location: Cincinnati
BW Attendees: Amy | Biko | Alex
External Attendees: 5
Category | Task | Owner | Deadline | Status | Existing Resources | Notes
Planning & Admin | [5 empty] | Something like SteerCo template can help schedule (https://docs.google.com/spreadsheets/d/1pP_PnkgTsC00I4yI_4lf2Iixn7LrhmbEOQjDWF_Ny-I/edit?usp=drive_link)
| Identify a final date and hold on calendars |  | 2025-12-11
| Communicate date and give travel parameters to rest of project team |  | 2025-12-11
Agenda & Facilitation
Draft event agenda and timing
| Develop a plan to send prework |  | 2025-12-11
Contracts |  |  |  |  | Cvent (cvent.com/venues) can help research and submit venue RFPs | Reminder about BW contracts policy
| Research and shortlist 5 event venues |  | 2025-12-25 |  |  | A table/comparison tool within your PM doc can be helpful
Finalize venue choice and solicit final contract
| Submit venue contract for BW review |  | 2026-01-08
Secure signatures and finalize venue contract
Meeting Space & A/V | [5 empty] | Reminder about BW contracts policy
Confirm meeting room setup and A/V needs
| Solicit and finalize any BEOs |  |  |  |  | Reminder about BW contracts policy
Lodging | [5 empty] | Hotels usually require 10+ rooms for room blocking. BW typically responsible to fill 80% of those rooms. Rooms can be paid all on one card (submit master booking list), or hotel can generate booking link.
Ensure sleeping rooms are part of venue contract
| Book sleeping rooms for attendees |  | 2026-01-08
Share lodging confirmation details
Meals |  |  |  |  | EZ Cater can help you with group orders and catering (ezcater.com) | 19 vegetarians
| Solicit dietary needs from external attendees |  | 2026-02-05
| Plan menus accommodating dietary needs |  |  |  |  | There's an existing prompt in our dashboard that can help!
| Research offsite dinner venues |  |  |  |  | There's an existing prompt in our dashboard that can help!
| Finalize venue choice and solicit final contract |  |  |  |  | Reminder about BW contracts policy
Submit venue contract for BW review
Secure signatures and finalize venue contract
Solicit and finalize any BEOs
Materials & Shipping
| Prepare name badges and materials |  | 2026-02-12
Order fidget toys or other engagement tools
Ship supplies to venue
Onsite
| Gather and list Onsite Contact name and number |  | 2026-02-26
Post-Event
Conduct internal debrief and lessons learned
| Ensure all expenses are accounted for |  | 2026-03-12 |  |  | A budget tracker within your PM doc is helpful